## Sheet1
Cost Estimate
Project Name: | Date:
Note: Enter your WBS and costs each month. Add/delete rows and columns as needed and check all formulas (bolded below).
Month
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | Total Cost
WBS Categories
1. Initiating | 13000 | [11 empty] | 13000
2. Planning | 6000 | 16000 | 8000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 |  |  |  | 36000
3. Executing |  |  | 0 |  |  | 0 | 0 | [5 empty] | 0
3.1 Course design and development |  |  | 0 |  |  | 0 | 0 | [5 empty] | 0
3.1.1 Supplier management training |  |  | 5000 | 73666.6667 | 73666.6667 | 73666.6667 | [6 empty] | 226000
3.1.2 Negotiating skills training |  |  | 5000 | 35500 | 35500 | 35500 | [6 empty] | 111500
3.1.3 Project management training |  |  | 5000 | 43000 | 43000 | 43000 | [6 empty] | 134000
3.1.4 Software applications training |  |  | 5000 | 43000 | 43000 | 43000 | [6 empty] | 134000
3.2 Course administration | [5 empty] | 17000 | 53333.3333 | 53333.3333 | 53333.3333 |  |  |  | 177000
3.3.Course evaluation | [6 empty] | 3000 | 3000 | 3000 | 7500 |  |  | 16500
3.4 Stakeholder communications |  | 1500 | 1500 | 1500 | 1500 | 1500 | 1500 | 1500 | 1500 | 1500 | 1500 | 1500 | 16500
4. Monitoring and Controlling | 1000 | 2000 | 2000 | 2000 | 3000 | 3500 | 3000 | 3000 | 2000 | 3000 | 2000 | 1000 | 27500
5. Closing | [10 empty] | 8000 | 3000 | 11000
Subtotal | [12 empty] | 903000
Reserves* |  |  | 0 |  |  | 0 | 0 |  |  |  |  | 90300 | 90300
Total | 20000 | 19500 | 31500 | 199666.6667 | 200666.6667 | 218166.6667 | 61833.3333 | 61833.3333 | 60833.3333 | 12000 | 11500 | 95800 | 993300
*Reserves are all entered in month 12